## 工作表1
功能 | Linebot開啟指定格子 | Linebot排程開啟時間 | Webcam | FaceRecognize
細項 | Line.py | Line.py | Line.py | Line.py
Finish % | 100% | 0% | 100% | 0%
DeadLine | None | 2022-10-12 | None | 2022-10-12
細項 | PWM.py | schedule.py | Server.py | Recognize.py
Finish % | 90% | 0% | 100% | 50%
DeadLine | 2022-10-12 | 2022-10-12 | None | 2022-10-12
細項 | Environment | Environment | Environment | Environment
Finish % | 100% | 0% | 0% | 0%
DeadLine | 2022-10-12 | 2022-10-12 | 2022-10-12 | 2022-10-12